CERTIFIED PROJECT

MANAGEMENT PRACTITIONER

C P M P

Detailed Syllabus

Learning outcomes, indicative content, and assessment

Mapped to the African Context Project Management Body of Knowledge

African Institute of Project Assurance and Forensics

Edition 2026

# Contents

Foreword3

Part One  |  Using this Syllabus4

1.1  What the syllabus covers4

1.2  How it maps to the examinations4

1.3  Levels of learning and command verbs4

1.4  Weighting and the pass standard5

Part Two  |  The Shared Foundation6

Part Three  |  Paper P1: Delivery Planning and Control7

P1.1  Initiation and business case7

P1.2  Scope and requirements7

P1.3  Schedule and time8

P1.4  Cost, budget, and funding8

P1.5  Quality9

P1.6  Risk and uncertainty9

Part Four  |  Paper P2: Delivery Practice and Governance11

P2.1  Integration and delivery governance11

P2.2  Assurance-ready controls11

P2.3  Procurement and contract administration12

P2.4  Resources and capacity12

P2.5  Stakeholder, community, and communications13

P2.6  Benefits realisation and sustainability13

Part Five  |  The Competency Assessment15

Part Six  |  Assessment Weighting and the Pass Standard16

Appendix  |  Command Verbs17

# Foreword

This syllabus sets out what a candidate for the Certified Project Management Practitioner must know and be able to do. It takes the twelve knowledge domains of the African Context Project Management Body of Knowledge and turns each into learning outcomes and indicative content that can be taught and examined. Where the Body of Knowledge explains why African delivery conditions matter, this syllabus states plainly what a candidate must be able to do about them.

It is written for three readers at once. For the candidate, it is a map of what to learn and the standard to reach. For the trainer, it is the specification a course must cover. For the examiner, it is the source of what may fairly be tested and how. The three should always be looking at the same thing, and this document is that thing.

# Part One  |  Using this Syllabus

## 1.1  What the syllabus covers

The CPMP certifies competence to deliver projects to the Institute’s standard in the conditions African practice presents. This syllabus covers the delivery-specific knowledge that the credential tests. It builds on the shared foundation that every candidate passes first, and it does not repeat it. A candidate is assumed to have the global fundamentals of project management already, so the syllabus concentrates on applying them well in the African context rather than teaching them from the start.

## 1.2  How it maps to the examinations

The twelve knowledge domains are examined across two written papers and one competency assessment, as set out in the Credential Specification. The planning and control domains sit in the first paper. The integration, governance, enabling, and value domains sit in the second. The competency assessment then asks the candidate to bring all of it together on a single project. The table below shows the map.

| Assessment | Domains examined |
| --- | --- |
| P1 Delivery Planning and Control | Initiation and business case; scope; schedule; cost, budget, and funding; quality; risk. |
| P2 Delivery Practice and Governance | Integration and governance; assurance-ready controls; procurement; resources and capacity; stakeholder and community; benefits and sustainability. |
| C Competency Assessment | All twelve domains, integrated in a delivery plan and governance pack for a set project brief. |

## 1.3  Levels of learning and command verbs

The CPMP is a practising credential, so most of what it tests sits at the higher levels of learning. A candidate is rarely asked only to recall a fact. They are asked to apply, to analyse, and to judge. The syllabus uses three levels, and the command verbs in each learning outcome signal the level at which it is pitched. The full list of verbs is in the appendix.

- Know. Recall and state established facts and definitions. Define, list, identify.

- Understand. Explain how and why something works, and distinguish between things. Explain, describe, distinguish.

- Apply and evaluate. Use knowledge in a real situation, analyse it, and reach a judgement. Prepare, develop, assess, manage, justify, recommend.

## 1.4  Weighting and the pass standard

Each paper carries a weighting across its domains, shown at the head of Parts Three and Four, so that a course and a candidate can see where the emphasis falls. The pass mark for each written paper is fifty per cent, and the competency assessment must be passed on its own terms. A candidate must pass all three, and the shared foundation before them, to be certified. The detail of examination format, resits, and time limits is in the Credential Specification and is not repeated here.

# Part Two  |  The Shared Foundation

Before any candidate reaches the CPMP papers, they pass the shared foundation that every designation of the Institute rests on. It is set out in full in the Credential Specification, and it is a prerequisite for everything in this syllabus. It is named here only so that the whole path is visible in one place.

- Principles of Project Delivery. The lifecycle, governance, financing, procurement, and controls of projects, with attention to African delivery conditions.

- Evidence and Method. Gathering, handling, and weighing evidence to a standard that withstands scrutiny.

- Professional Ethics and Independence. The code of conduct, the duties of independence and public interest, and the delivery-scrutiny separation. Mandatory, and never waived.

The foundation does the groundwork. This syllabus assumes it throughout and builds the delivery-specific competence on top of it.

# Part Three  |  Paper P1: Delivery Planning and Control

The first paper tests the domains through which a project is planned and kept under control: how it is justified, scoped, scheduled, costed, assured for quality, and managed for risk. These are the disciplines a practitioner uses to build a credible plan and hold a project to it, and in the African context each is reshaped by the conditions the Body of Knowledge describes. The weighting across the paper is shown below.

| Module | Domain | Weight |
| --- | --- | --- |
| P1.1 | Initiation and business case | 12% |
| P1.2 | Scope and requirements | 14% |
| P1.3 | Schedule and time | 20% |
| P1.4 | Cost, budget, and funding | 24% |
| P1.5 | Quality | 12% |
| P1.6 | Risk and uncertainty | 18% |

### P1.1  Initiation and business case

AIM

To prepare and appraise a business case that establishes a project’s need, outcome, and deliverability for the funders and sponsors who must approve it.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- establish and articulate the need a project is intended to meet, and the outcome it will deliver;

- prepare a business case that satisfies the logic of development financiers and public sponsors, not commercial return alone;

- state and test the assumptions on which the case rests, and show their effect on viability;

- appraise options, including the do-nothing case, and justify a recommended way forward.

INDICATIVE CONTENT

- purpose and structure of a business case: need, outcome, and benefit;

- options appraisal and the treatment of the do-nothing case;

- the appraisal expectations of development funders and public sponsors;

- assumptions, sensitivities, and the honest treatment of uncertainty.

IN THE AFRICAN CONTEXT

The case must often carry a development rationale and satisfy a funder’s own appraisal rules, and it must be honest about the data and assumptions behind it rather than presenting a confidence the evidence does not support.

### P1.2  Scope and requirements

AIM

To define and control project scope and requirements where the information to do so is often incomplete.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- elicit and define requirements, and translate them into a controllable scope;

- document the assumptions and baseline data that the scope depends on;

- establish a change-control approach proportionate to the project;

- manage the scope change that weak initial data and a shifting institutional environment make likely.

INDICATIVE CONTENT

- requirements definition; the scope statement and breakdown;

- baselining, configuration, and the assumptions log;

- change control and its governance;

- managing scope under uncertainty.

IN THE AFRICAN CONTEXT

Scope is frequently set against thin baseline data and against demands that shift with personnel and politics, so disciplined control and honest assumption-tracking matter more here than where the ground is firmer.

### P1.3  Schedule and time

AIM

To develop and control a credible schedule built around the real constraints of African delivery.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- develop a schedule that reflects disbursement, seasonal access, statutory approvals, and logistics;

- identify the critical path and the constraints that most threaten it;

- apply appropriate estimating and contingency to time;

- monitor progress and forecast completion honestly.

INDICATIVE CONTENT

- scheduling techniques, the critical path, and float;

- time estimating and contingency;

- disbursement-linked and season-linked scheduling;

- progress monitoring and forecasting.

IN THE AFRICAN CONTEXT

A credible schedule is built around the rhythm of disbursement, the closing of sites by season, the sequence of approvals, and the length of supply chains, rather than in spite of them.

### P1.4  Cost, budget, and funding

AIM

To plan and control cost in a multi-source, multi-currency funding environment where cash availability, not budget approval, is the real constraint.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- prepare a cost estimate and budget with appropriate contingency;

- plan and manage cash flow against disbursement reality rather than approved budget;

- identify and carry exchange-rate and counterpart-funding exposure explicitly;

- monitor, control, and forecast cost, using earned value where it fits.

INDICATIVE CONTENT

- estimating, budgeting, and cost contingency;

- cash-flow planning and disbursement management;

- multi-currency funding and exchange-rate exposure;

- counterpart funding; cost control, earned value, and forecasting.

IN THE AFRICAN CONTEXT

Cost management here is inseparable from funding management. Disbursement lag, uncertain counterpart funding, and currency movement can undo good cost control, so the funding structure is itself an object the practitioner manages.

### P1.5  Quality

AIM

To set and hold quality standards through a shallow supply market and variable inputs.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- define fit-for-purpose quality requirements and acceptance criteria;

- plan quality assurance and control proportionate to the project;

- manage the quality risk that a limited supplier pool and variable materials create;

- manage non-conformance and rework, and their magnified cost at distance.

INDICATIVE CONTENT

- quality planning, assurance, and control;

- acceptance criteria and inspection;

- supplier quality and materials variability;

- non-conformance, rework, and improvement.

IN THE AFRICAN CONTEXT

Quality must be assured where capable suppliers are few and inputs vary, and where the cost of getting it wrong is magnified by distance and by the scarcity of the resources needed to put it right.

### P1.6  Risk and uncertainty

AIM

To identify, assess, and manage the distinctive risk profile of African delivery.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- identify and assess risk across currency, political, institutional, capacity, and counterpart-funding exposures;

- prepare proportionate responses and set contingency accordingly;

- distinguish quantifiable risk from deeper uncertainty, and plan for both;

- monitor risk and maintain the risk record through delivery.

INDICATIVE CONTENT

- risk identification, assessment, and response;

- the African risk profile: political and currency risk;

- contingency and resilience;

- risk monitoring and the risk register.

IN THE AFRICAN CONTEXT

The risk weighting sits towards currency movement, political and institutional change, supply-market capacity, and the reliability of counterpart funding. These are carried explicitly, not treated as background conditions to be discovered late.

# Part Four  |  Paper P2: Delivery Practice and Governance

The second paper tests the domains through which a project is held together, enabled, governed, and made to deliver lasting value: integration across many parties, the controls that make delivery auditable, procurement, resources and capacity, stakeholder and community engagement, and the realisation of benefit. This is where much of what the African context adds is carried, and where the Institute’s distinctive discipline of assurance-ready delivery sits. The weighting across the paper is shown below.

| Module | Domain | Weight |
| --- | --- | --- |
| P2.1 | Integration and delivery governance | 16% |
| P2.2 | Assurance-ready controls | 18% |
| P2.3 | Procurement and contract administration | 20% |
| P2.4 | Resources and capacity | 12% |
| P2.5 | Stakeholder, community, and communications | 20% |
| P2.6 | Benefits realisation and sustainability | 14% |

### P2.1  Integration and delivery governance

AIM

To integrate a project and govern it across a fragmented landscape of institutions and funders.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- establish clear decision rights and governance across multiple clients and funders;

- keep a funding coalition aligned through delivery;

- steer a project through the sequence of external approvals it depends on;

- integrate the knowledge areas into a coherent, controllable whole.

INDICATIVE CONTENT

- project governance and decision rights;

- managing a multi-institution client and a funder coalition;

- approval sequencing and interface management;

- integration across the knowledge areas.

IN THE AFRICAN CONTEXT

Integration here is less about coordinating inside one client and more about holding a coalition together and winning approvals in the right order, because the project rarely answers to a single coherent authority.

### P2.2  Assurance-ready controls

AIM

To deliver in a way that is governance-ready and auditable, so a project can be assured while it runs and examined after.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- establish and maintain the records, controls, and evidential trail of delivery;

- show, at any point, where a project stands and why, on the evidence;

- prepare a project for independent assurance and for possible forensic examination;

- maintain the separation between delivery and independent scrutiny.

INDICATIVE CONTENT

- delivery records and the audit trail;

- controls and the evidence that supports them;

- assurance-readiness and forensic defensibility;

- the delivery-scrutiny separation in practice.

IN THE AFRICAN CONTEXT

This is the discipline that distinguishes the Institute’s approach to delivery. A project delivered this way can show at any moment not only where it stands but why, and it connects delivery to the assurance and forensic work of the wider profession.

### P2.3  Procurement and contract administration

AIM

To procure lawfully and effectively within public procurement law and a thin supply market, and to administer contracts with disputes in view.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- plan and conduct procurement within national procurement law and local-content rules;

- test the depth and capacity of the supply market before relying on it;

- administer contracts, variations, and claims fairly;

- anticipate and manage the disputes the environment makes more likely.

INDICATIVE CONTENT

- public procurement law, thresholds, and approvals;

- local content; market and supplier assessment;

- contract types and administration; variations and claims;

- dispute avoidance and management.

IN THE AFRICAN CONTEXT

Procurement law is a fixed part of the delivery timetable rather than an obstacle to work around, the contractor pool is often shallow, and disputes are more likely, so contracts are administered with that likelihood in mind from the start.

### P2.4  Resources and capacity

AIM

To secure the resources a project needs where they may be scarce, and to build capacity as part of delivering the work.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- plan and secure the human and physical resources delivery requires;

- assess resource scarcity and plan around it;

- build capacity deliberately where it is absent, rather than assuming it is available;

- manage and control resources through delivery.

INDICATIVE CONTENT

- resource planning and acquisition;

- scarcity and its management;

- capacity building as part of delivery;

- resource control.

IN THE AFRICAN CONTEXT

Capacity cannot be assumed to be sitting ready to hire. Competent delivery often has to strengthen the ability to deliver as it goes, so that the project leaves more capability behind than it consumed.

### P2.5  Stakeholder, community, and communications

AIM

To secure and sustain the consent of communities and customary authorities, and to hold together the coalition a project depends on.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- identify and analyse stakeholders across funders, institutions, communities, and the informal economy;

- secure and sustain community and customary consent to build;

- plan and conduct engagement that is legitimate in its cultural setting;

- communicate effectively across a diverse coalition through delivery.

INDICATIVE CONTENT

- stakeholder identification and analysis;

- customary land, community consent, and traditional authority;

- the informal economy and its interface with the project;

- engagement and communications planning.

IN THE AFRICAN CONTEXT

Consent is negotiated with communities and customary authorities and must be maintained, because a community that withdraws its cooperation can halt a project as surely as a funder that withdraws its money. Engagement is a core discipline, resourced from the first day to the last.

### P2.6  Benefits realisation and sustainability

AIM

To ensure the change a project was undertaken to deliver actually arrives, lasts, and withstands the conditions around it.

LEARNING OUTCOMES: THE CANDIDATE IS ABLE TO

- plan for and secure the intended benefit beyond practical completion;

- embed the environmental and social performance that funders and communities require;

- build resilience to a shifting climate into delivery;

- plan for the operation, maintenance, and handover of what is built.

INDICATIVE CONTENT

- benefits planning and realisation;

- environmental and social safeguards and ESG;

- climate resilience and adaptation;

- operation, maintenance, and sustainable handover.

IN THE AFRICAN CONTEXT

A project that hands over an asset but not the capacity to run it, or one that cannot withstand the next flood, has not succeeded. Benefit and resilience are planned for from the start, not bolted on at the end.

# Part Five  |  The Competency Assessment

The written papers test the domains one by one. The competency assessment tests whether a candidate can bring them together on a real project, which is the thing the credential ultimately certifies. It is where knowing the parts becomes being able to do the work.

## 5.1  The task

The candidate is given a project brief and asked to produce a delivery plan and governance pack for it. The brief describes a project set in recognisable African delivery conditions, with the funding structure, institutional setting, community context, and physical environment that the Body of Knowledge describes. The candidate must read those conditions and produce a plan that answers them, not a generic plan that ignores them.

## 5.2  What the pack must contain

The delivery plan and governance pack is expected to cover, in proportion to the brief, the planning and control disciplines of P1 and the practice and governance disciplines of P2, integrated into one coherent response. It is assessed less on length than on judgement: whether the candidate has read the context correctly and planned for it.

## 5.3  How it is marked

The assessment is marked against six criteria, each carrying equal weight.

- Contextual reading. Has the candidate correctly identified which contextual pressures bear on this project, and how hard?

- Planning and control. Are the scope, schedule, cost, quality, and risk sound and internally consistent?

- Governance and assurance-readiness. Would this project be auditable, and could it be independently assured?

- Stakeholder and community. Is consent secured and sustained, and is engagement legitimate and resourced?

- Feasibility and coherence. Does the plan hold together, and could it actually be delivered as written?

- Professional judgement. Does the pack show the judgement of a practitioner, not the recall of a student?

# Part Six  |  Assessment Weighting and the Pass Standard

The three CPMP assessments are examined and passed independently. The written papers carry the domain weightings shown at the head of Parts Three and Four. Across the credential as a whole, the three assessments contribute as set out below, and a candidate must pass each on its own terms, and the shared foundation before them, to be certified.

| Assessment | What it tests | Contribution | Pass mark |
| --- | --- | --- | --- |
| P1 Delivery Planning and Control | The six planning and control domains. | 30% | 50% |
| P2 Delivery Practice and Governance | The six practice and governance domains. | 30% | 50% |
| C Competency Assessment | All twelve domains, integrated on one project. | 40% | Pass on its own terms |

A word on why the competency assessment carries the most The written papers can confirm that a candidate knows the domains. Only the competency assessment can show whether they can put them together and deliver in the conditions that actually obtain. Because that integrated judgement is what the CPMP certifies, it carries the largest single share.

# Appendix  |  Command Verbs

The command verbs used in the learning outcomes signal the level of learning each one expects. They are grouped here by level, so that candidates, trainers, and examiners read them the same way.

### Know

Define, list, identify, state, name, recall. Used where the candidate must reproduce established facts and definitions.

### Understand

Explain, describe, distinguish, illustrate, summarise, compare. Used where the candidate must show they grasp how and why something works, not only that it does.

### Apply and evaluate

Prepare, develop, produce, plan, apply, manage, control, assess, analyse, evaluate, justify, recommend. Used where the candidate must use knowledge in a real situation, reach a judgement, and defend it. Most CPMP outcomes sit here, because the credential certifies a practitioner, not a student.

African Institute of Project Assurance and Forensics (AIPAF)

Certified Project Management Practitioner: Detailed Syllabus  •  Edition 2026